## Program Risk Log
GEMMA Program Risk Register C-GPM-001
Part I. Risk Identification | [5 empty] | Part II. Risk Analysis for Existing Controls |  |  | Part III. Risk Response
Name | Program Risk Category | Risk Description (ignoring controls) | Impact 1-5 (ignoring controls) | Likelihood 1-5 (ignoring controls) | Total Risk Score Low = 1 - 8 Med = 9 - 16 High = 17 - 25 | What Controls (if any) are currently in place? | Control Effectiveness 1-5 | Residual Risk Score Low = 1 - 8 Med = 9 - 16 High = 17 - 25 | Control or Risk Mitigation Strategy | Control effectiveness based on mitigation strategy 1-5 | Residual Mitigated Risk Low = 1 - 8 Med = 9 - 16 High = 17 - 25 | Contingency Plan | Cost of contingency plan | Owner | Review Due Date | Status
Program/Project Resources | Schedule | Unable or delay in hiring the specialized resources when needed because there is a shortage of qualified people, the program delivery could be negatively affected. | 3 | 2 | 6 | None | 5 | 5.94 | Increase M&O staff time on Gemma | 3 | 3 | 1) Work with PM to reorder team member's tasks to maintain critical path, 2) reduce |  | PM | 2018-12-31 | Open
Program/Project Resources | Schedule | If existing resources are not assigned to the project because of competing priorities then program delivery could be negatively impacted | 2 | 2 | 4 | The Resource Allocation Process | 2 |  | Watch project portfolio for any at risk projects that could cause the risk and recommend coaching for project teams. | 3 |  | Escalate to Directorate |  | PM |  | Open
Program/Project Resources | Scope | If costs of staff from CSA1 exceed available funding in CSA2 projects may need to down scope delivering less than promised | 2 | 2 | 4 | Monitoring costs in control and other costs in casnet | 5 | 3.96 | Reduce and shift other line items between projects | 4 | 3 | 1) Work with PM to reorder team member's tasks to maintain critical path, 2) reduce scope to meet project due date |  | PM |  | Open
Procurements | Schedule | If procurements cannot be completed in a timely manner because insufficient aquisition planning, business services staff shortages or NSF delayed approvals then the program delivery could be negatively affected | 4 | 2 | 8 | None | 5 | 7.92 | Work with Cas on ways to streamline process beneficial to both parties | 2 | 2 | Escalate to AURA corporate; Contract with a temp agency | $13k per mth. | PM | 2018-12-31 | Open
Communications | Benefits | If Gemini and AURA, the STAC, the Governance Board, and the user community are not aligned because of miscommunication then the long term goals may not be met. | 4 | 2 | 8 | Governance reports and meetings, User committee | 2 | 2 | Create a communications advisory board | 4 | 6 | Hire marketing firm | $50 per hour | PM | 2019-05-30 | Open
Communications | Benefits | If team communication isn't effective and the team is not aligned, schedule will be impacted. | 5 | 3 | 15 | Escalation to appropriate manager to help resolve communication concerns. | 5 | 14.85 | Clearly defined roles, responsibilities and expectations. | 5 | 14.85 | Escalate to program board. | Schedule may be impacted | PM | 2019-05-30 | Open
Note on C3: If [realized risk] because [trigger] then [impact]
Note on D3: Low to high
Note on E3: Low to high
Note on H3: 1 = sufficient control; 5 = no control
Note on K3: scale of 1 (very effective) to 5 (minimal effectiveness)

## Closed risks
MOVE CLOSED RISKS INTO THIS TAB
Part I. Risk Identification | [5 empty] | Part II. Risk Analysis for Existing Controls |  |  | Part III. Risk Response
Name | Program Risk Category | Risk Description (ignoring controls) | Impact 1-5 (ignoring controls) | Likelihood 1-5 (ignoring controls) | Total Risk Score Low = 1 - 8 Med = 9 - 16 High = 17 - 25 | What Controls (if any) are currently in place? | Control Effectiveness 1-5 | Residual Risk Score Low = 1 - 8 Med = 9 - 16 High = 17 - 25 | Control or Risk Mitigation Strategy | Control effectiveness based on mitigation strategy 1-5 | Residual Mitigated Risk Low = 1 - 8 Med = 9 - 16 High = 17 - 25 | Contingency Plan | Cost of contingency plan | Owner | Review Due Date | Status
Program Costs | Cost | If the funding does not cover the costs then current program scope will need to change | 3 | 3 | 9 | None | 2 | 2.25 | Rebudgeting eliminating activites and or capabilities |  |  | Shift under utilized resources from other projects. Rebudgeting approved by Directorate creating managment budget. |  | PM | 2019-02-26 | Closed
Government shutdowns | Resources | If the gov. shuts down & AURA HR has to delay job offers for PM and SE the project may go beyond the CSA POP. | [9 empty] | Government shutdown ended with some affect on hiring and contracts. New hires could not be made offers until end of shutdown. |  |  | 2019-02-15 | Closed
Note on C3: If [realized risk] because [trigger] then [impact]
Note on D3: Low to high
Note on E3: Low to high
Note on H3: 1 = sufficient control; 5 = no control
Note on K3: scale of 1 (very effective) to 5 (minimal effectiveness)

## Grading Criteria
NOTE: Each project owns customizing this worksheet to criteria that makes sense for their project.
Impact - Scale
Impact Criteria | 1 | 2 | 3 | 4 | 5
Technology Risk | Known technology |  | Known technical foundation |  | State of the art technology
Resource Competency / availability | Competency in-house |  | Some in-house / some known external |  | Minimal to no in-house knowledge
Strategic / Telescope interruption or Competitive Disadvantage | Low Severity (Manual process could recover) |  | Medium Severity |  | High Severity or Business Stop
Schedule | Schedule well understood |  | Schedule has some unknowns |  | Schedule is not well understood
Financial loss | <=$250K |  | $250k - $5M |  | >=$5M
Scope | Scope well understood; no change requests submitted |  | Scope gaps exist in non-critical areas. Some change requests submitted or expected | N/A | Scope not well defined. Change requests inevitable
Likelihood - Scale
Likelihood Criteria | 1 | 2 | 3 | 4 | 5
Probability | 0% | 25% | 50% | 75% | 100%
Descriptive | Remote |  | Probably |  | Certain
Controls Effectiveness - Scale
| 1 | 2 | 3 | 4 | 5
Weight for calc purposes, DO NOT CHANGE | 99% | 75% | 50% | 25% | 1%
Descriptive | Existing - Sufficient |  | Existing - Non Sufficient |  | Non-Existent